## Sheet1
All tasks
Task no. | Task title | Planned start date | Planned end date
1 | Investigate and analayze HTML components of this project | 2021-08-27 | 2021-09-27
2 | Modify HTML components to add features based on suggestions from our designers | 2021-09-05 | 2021-12-01
3 | Separate Search and Record layer from HTML components | 2021-09-05 | 2021-09-22
4 | Rewrite the schemas for repository and project database | 2021-10-15 | 2021-12-15
5 | Change the format of JSON output file of search result | 2021-10-17 | 2021-11-15
6 | Investigate on backend components of this project (such as querying, elastic search) | 2021-08-27 | 2022-01-05
7 | Improve the efficiency of elastic search | 2022-01-05 | 2022-01-30
8 | Change the input parsing method when keywords are sent from HTML | 2021-11-05 | 2022-01-03
9 | Fix the bug of short-live SQL connection object when querying the database | 2021-10-01 | 2021-10-15
10 | Setup, manage, and maintain the GIT environment of this project | 2021-08-27 | 2021-09-15
Milestone no. | Milestone detail | Planned start date | Planned end date
1 | Finish all HTML static design | 2021-08-27 | 2021-12-01
2 | Complete the backend logic for elastic search | 2021-08-27 | 2022-01-05
3 | Integrate the backend logic into HTML design | 2022-01-05 | 2022-04-01